AVSAR - Startup-Friendly Public Procurement Platform

Project Management Plan

How the AVSAR programme is planned, executed, controlled and closed

Document control

| Field | Value |
| --- | --- |
| Document ID | AVSAR-PMP-003 |
| Version | 1.0 |
| Date | 03 September 2026 |
| Prepared by | TandSol |
| Status | Baselined |
| Related documents | AVSAR-HBK-001, AVSAR-CHR-002, AVSAR-RTM-004, AVSAR-SDD-005, AVSAR-CDR-006, AVSAR-RSK-007, AVSAR-TML-008, AVSAR-DPD-009, AVSAR-RET-010, AVSAR-QAB-011 |
| Classification | Internal - Smart India Hackathon submission |

## Purpose of this document

This plan states how the work authorised by AVSAR-CHR-002 is actually run: the delivery approach, the schedule and its critical path, how scope changes are handled, how quality is assured, how risk is managed, who communicates what to whom, and what closure means. It is the operational counterpart to the Charter: the Charter says what and why, this document says how.

## Revision history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 1.0 | 03 Sep 2026 | TandSol | Baseline for the Smart India Hackathon submission. |

## Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor | Mission Director |  |  |
| Project Manager | TandSol |  |  |

# 1. Delivery approach

The programme is delivered in sixteen phases over fourteen weeks to submission, followed by two quarters of deployment readiness. Nine of the sixteen phases run in parallel, which is what allows a five-stage mechanism with seven roles to be built and tested inside a single quarter.

Three sequencing rules govern the plan:

Policy before design. The statutory basis is mapped and confirmed before any schema is written, because the eligibility gate and the procurement modes are the design. Getting the rule wrong invalidates everything downstream.

Workflow before features. Every legal state transition is declared and frozen before route handlers are written. A state machine discovered incrementally through handlers is a state machine nobody can review.

Design system before screens. The token and component layer is built alongside the API so that no screen is ever blocked on styling decisions, and so that twenty-four routes look like one product rather than twenty-four.

## 1.1 Work breakdown

| Level 1 | Level 2 | Phases |
| --- | --- | --- |
| 1 Policy and requirements | Statutory mapping, Charter, RTM baseline | P1, P2 |
| 2 Architecture | Data model, workflow state machines, design system | P3, P4 |
| 3 API construction | Identity and challenge; evaluation and pilot; procurement and registry; audit and transparency | P5, P6, P7, P8 |
| 4 Client construction | Public site; role workspaces | P9, P10 |
| 5 Data and verification | Seed dataset, end-to-end suite, accessibility and security pass | P11, P12, P14 |
| 6 Documentation and submission | Document set, demonstration, submission | P13, P15 |
| 7 Deployment readiness | Live verification, single sign-on, PostgreSQL, integrations, VAPT, accessibility audit | P16 |

## 1.2 Critical path

P1 policy mapping to P2 requirements to P3 data model and workflow to P5 identity and challenge API to P6 evaluation and pilot API to P12 end-to-end suite to P15 submission. The design-system and client phases run alongside the API and are not on the critical path; a one-week slip in either is absorbable, whereas a one-week slip in P3 or P6 moves the submission date.

Schedule detail: Phase dates, durations, owners, sequential or parallel mode, and a week-level Gantt are maintained in AVSAR-TML-008. That workbook is the schedule of record; this section states the approach, not the dates.

# 2. Scope management

Scope is defined in AVSAR-CHR-002 section 4 and decomposed into requirements in AVSAR-RTM-004. No work is undertaken that does not trace to a requirement, and no requirement is admitted that does not trace to a Charter objective.

## 2.1 Change control

| Step | Action | Owner |
| --- | --- | --- |
| 1 | Raise the change against the affected requirement ID, stating the objective it serves | Requester |
| 2 | Assess the effect on the critical path, the RTM and the Risk Register | Project Manager |
| 3 | Decide: accept, defer to a later phase, or reject with the reason recorded | Sponsor for a scope change; Project Manager within scope |
| 4 | Update AVSAR-RTM-004 with the new or amended row in the same turn as the decision | Project Manager |
| 5 | Version-increment every affected document with a dated revision note | Project Manager |

Deprecation convention: A withdrawn requirement keeps its row and its ID in the RTM. The description is prefixed [DEPRECATED - reason] rather than deleted, so historical traceability is never broken by renumbering.

# 3. Quality management

## 3.1 Definition of done

A unit of work is complete only when all five hold:

| # | Gate | Evidence |
| --- | --- | --- |
| 1 | It parses, imports resolve, no undefined references | Production build completes with no error |
| 2 | Happy path and at least one edge case behave correctly | An assertion in the end-to-end suite, or a recorded manual pass |
| 3 | No injection, no cross-site scripting, parameterised SQL, secrets in the environment | Security RTM row moved to Verified |
| 4 | Web-visible behaviour confirmed in a running application | Screen exercised against a live API, not only against a test |
| 5 | Code Register and RTM updated in the same turn as the change | AVSAR-CDR-006 row present; RTM status advanced |

## 3.2 Verification approach

| Layer | Method | Coverage |
| --- | --- | --- |
| Statutory rules | Assertion against each gate with both a passing and a failing case | Eligibility, fit, ceiling, payout total, DPDP precondition, evidence gate |
| Workflow | Assertion that a legal transition succeeds and an illegal one returns 409 | All four state machines |
| Authorisation | Cross-role assertion that a forbidden call returns 403 | Publication authority, sanction authority, cross-department reads |
| Integrity | Full-chain audit verification after a complete lifecycle run | Every state change written during the run |
| Client | Manual pass per role against a live API | All twenty-four routes |
| Build | Production build as a compile check across every module | 872 modules |
| Accessibility | Keyboard traversal, contrast check, screen-reader review | Public site and all seven workspaces |

The end-to-end suite is the primary quality gate. It runs against a live API on a throwaway database and walks one problem statement through all five stages, asserting thirty-two conditions including every refusal the mechanism depends on. A change that breaks a gate breaks the suite.

## 3.3 Quality metrics

| Metric | Target | Actual at baseline |
| --- | --- | --- |
| End-to-end assertions passing | 100% | 32 of 32 |
| Requirements verified | At least 85% | See AVSAR-RTM-004 Summary |
| Files registered in the Code Register | 100% | See AVSAR-CDR-006 Summary |
| Production build errors | Zero | Zero |
| Natively compiled dependencies | Zero | Zero |
| Chunks above 500 kB after minification | Zero | Zero |
| High-severity risks without a dated mitigation | Zero | See AVSAR-RSK-007 Summary |
| Compliance obligations with no evidence recorded | Zero | See AVSAR-DPD-009 Summary |

# 4. Risk management

Risks are recorded in AVSAR-RSK-007, scored as likelihood multiplied by impact on a one-to-five scale, and banded High at fifteen or above, Medium from eight to fourteen, and Low from one to seven. Score and severity are spreadsheet formulas, so re-scoring a risk reclassifies it automatically and the register cannot drift out of agreement with itself.

| Severity | Review cadence | Escalation |
| --- | --- | --- |
| High | Weekly | Sponsor, with a dated mitigation and a named owner |
| Medium | Fortnightly | Project Manager |
| Low | At each phase gate | Monitored on the register |

A mitigation must name the control that addresses the risk, not an intention to address it. On this register, for example, the mitigation for an undeclared conflict of interest is the precondition the API enforces before accepting a score - not a statement that evaluators will be reminded to declare.

# 5. Communication plan

| Audience | What | Format | Cadence |
| --- | --- | --- | --- |
| Sponsor | Progress against milestones, high risks, decisions needed | One-page note plus the transparency board | Fortnightly |
| Nodal officers | New capability affecting authoring or shortlisting | Release note and a short walkthrough | On release |
| Startups | State change on a record they own | In-app notification | Immediate |
| Evaluators | Assignment and reconciliation requirement | In-app notification | Immediate |
| Delivery team | Priorities, blockers, review of the definition of done | Stand-up | Daily |
| Delivery team | Phase gate: RTM status, register updates, risk re-score | Phase review | At each phase boundary |
| Audit and oversight | Decision record for any transaction | Audit trail, self-service | On demand |
| Public | Funnel, cycle time, payment discipline, proven solutions | Public transparency board | Continuous |

# 6. Resource plan

| Role | Responsibility | Allocation |
| --- | --- | --- |
| Project Manager | Schedule, change control, document set, phase gates | Full time |
| Policy Lead | Statutory mapping, procurement modes, relaxation logic | Phases P1 to P3, then advisory |
| Solution Architect | Data model, workflow state machines, service boundaries | Phases P3 to P8 |
| Backend Engineer | API, domain services, audit, seed data | Phases P5 to P11 |
| Frontend Engineer | Design system implementation, public site, role workspaces | Phases P4, P9, P10 |
| Design Lead | Token layer, component patterns, accessibility policy | Phase P4, then advisory |
| QA Lead | End-to-end suite, accessibility and security pass | Phases P12, P14 |

## 6.1 Responsibility assignment

R responsible, A accountable, C consulted, I informed.

| Activity | PM | Policy | Architect | Backend | Frontend | QA | Sponsor |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Statutory mapping | A | R | C | I | I | I | I |
| RTM baseline | R | C | C | C | C | C | A |
| Data model and workflow | A | C | R | C | I | C | I |
| Design system | I | I | C | I | R | I | I |
| API construction | A | C | C | R | I | C | I |
| Client construction | A | I | C | C | R | C | I |
| End-to-end suite | A | I | C | C | C | R | I |
| Document set | R | C | C | C | C | C | A |
| Scope change decision | R | C | C | I | I | I | A |
| Submission | R | C | C | C | C | C | A |

# 7. Configuration management

Version control. Git, initialised at project start. One commit per logical change, typed as feat, fix, refactor, docs, chore or test, with a body explaining why where the change is not self-evident.

Environment configuration. All configuration is read from the environment. server/.env.example is committed as the template; .env itself is ignored. No credential, token or signing secret is ever committed.

Database. The schema is the single source of truth in server/src/db/schema.sql, applied idempotently at boot. The seeded database file is ignored by version control so a developer's working data never enters a commit.

Documents. Every document carries a Document ID, a version and a dated revision note. The nine binary documents are generated from committed source in docs/tools, so a document and the data behind it cannot diverge.

Build artefacts. dist/ and node_modules/ are ignored. The production build is reproducible from a clean checkout with npm install and npm run build.

# 8. Procurement and third-party management

The reference implementation has no third-party engagement. Deployment readiness requires three, and each is a gate rather than a task:

| Engagement | Basis | Gate it satisfies |
| --- | --- | --- |
| VAPT by a CERT-In empanelled auditor | Empanelled-auditor list; limited tender | SR-017, D-23. No live award before completion. |
| Third-party GIGW 3.0 conformance audit | Limited tender among accessibility auditors | NF-008, D-24. No government-domain deployment before completion. |
| India-resident hosting and operations | Existing NIC or MeitY-empanelled cloud arrangement | D-19, D-21. Data residency and log retention. |

# 9. Monitoring and control

| Control | What is checked | When |
| --- | --- | --- |
| Phase gate | RTM statuses advanced, Code Register current, risks re-scored, definition of done met for every item in the phase | At each phase boundary |
| Build gate | Production build clean; no chunk above the size threshold | Every commit touching the client |
| Test gate | All end-to-end assertions pass | Before any commit touching a gate or a state machine |
| Document gate | Traceability chain intact: no requirement without a design reference or a test reference; no registered file without a design reference | At each phase boundary; formulas on the Summary tabs report it |
| Compliance gate | No obligation on AVSAR-DPD-009 without recorded evidence and a named owner | Every six months, and on any data-model change |

The document gate is machine-checked rather than eyeballed. The Summary tab of each workbook carries live formulas that count requirements missing a design reference, requirements missing a test reference, registered files missing a design reference, risks without a target date and obligations without evidence. Each must read zero for the phase gate to pass.

# 10. Closure

The programme closes on satisfaction of all seven criteria:

| # | Closure criterion | Verified by |
| --- | --- | --- |
| 1 | All Must-have requirements at status Verified | AVSAR-RTM-004 Summary |
| 2 | End-to-end suite green across every stage gate | npm test output |
| 3 | Every source file registered and traced | AVSAR-CDR-006 Summary |
| 4 | No High-severity risk without a dated mitigation and named owner | AVSAR-RSK-007 Summary |
| 5 | Every compliance obligation assessed with evidence or a dated remediation | AVSAR-DPD-009 Summary |
| 6 | Retention policy published with erasure triggers per data category | AVSAR-RET-010 |
| 7 | Document set baselined at version 1.0 with the traceability chain intact | This plan, section 9 |

Closure of the reference implementation is not closure of the mechanism. The deployment readiness phase carries its own gates, of which two are absolute: no live award may be made before VAPT is complete, and no government-domain deployment may occur before the accessibility audit is complete.