## Cover
AVSAR - Startup-Friendly Public Procurement Platform
Project Timeline
Document ID | AVSAR-TML-008
Version | 1.0
Date | 03 September 2026
Prepared by | TandSol
Status | Living
Related documents | AVSAR-HBK-001, AVSAR-CHR-002, AVSAR-PMP-003, AVSAR-RTM-004, AVSAR-SDD-005, AVSAR-CDR-006, AVSAR-RSK-007, AVSAR-DPD-009, AVSAR-RET-010, AVSAR-QAB-011
Classification | Internal - Smart India Hackathon submission
Purpose | Phase plan and week-level Gantt for the AVSAR programme, from policy mapping through the hackathon submission and on to deployment readiness. Phases marked Parallel overlap deliberately, which is what allows a five-stage mechanism to be built and tested inside a single quarter.
Revision history
Version | Date | Author | Change
1.0 | 03 Sep 2026 | TandSol | Baseline. Sixteen phases; fourteen weeks to submission plus two quarters of deployment readiness.
Critical path | P1 - P2 - P3 - P5 - P6 - P12 - P15. The design-system and client phases run alongside the API and are not on the critical path.
Milestones | M1 RTM baselined (01 Aug) - M2 schema and workflow frozen (15 Aug) - M3 API feature complete (08 Sep) - M4 client feature complete (12 Sep) - M5 end-to-end suite green (17 Sep) - M6 submission (30 Sep)

## Timeline
Phase | Phase name | Activities | Start | End | Duration (working days) | Owner | Mode
P1 | Discovery and policy mapping | Map the statutory basis; confirm which GFR relaxations apply and what they require on the file. Interview procurement and nodal officers on where a startup bid actually fails today. | 01 Jul 2026 | 18 Jul 2026 | 14 | Policy lead | Sequential
P2 | Charter and requirements | Write the Charter; derive and baseline the RTM; agree the five-stage model and the gate at each boundary. | 21 Jul 2026 | 01 Aug 2026 | 10 | Project manager | Sequential
P3 | Data model and workflow design | Seventeen-table schema; declare every legal state transition in one module; design the eligibility gate so each check cites its rule. | 04 Aug 2026 | 15 Aug 2026 | 10 | Solution architect | Sequential
P4 | Design system | Token layer, component layer, accessibility policy, dense-table and form patterns. Built in parallel with the API so screens are never blocked on styling. | 11 Aug 2026 | 22 Aug 2026 | 10 | Design lead | Parallel
P5 | API - identity and challenge | Authentication, role authorisation, startup registration with the statutory gate, problem statement authoring, approval and publication. | 18 Aug 2026 | 27 Aug 2026 | 8 | Backend engineer | Sequential
P6 | API - evaluation and pilot | Application submission through both gates, committee assignment, blind scoring with lock, pilot creation, DPDP precondition, milestones, KPI readings. | 25 Aug 2026 | 03 Sep 2026 | 8 | Backend engineer | Parallel
P7 | API - procurement and registry | Evidence-gated procurement with GFR modes, purchase orders, payment ledger with the statutory clock, Proven Solutions Registry and cross-department adoption. | 28 Aug 2026 | 05 Sep 2026 | 7 | Backend engineer | Parallel
P8 | Audit and transparency | Hash-chained audit trail and verification, public transparency board with the conversion funnel and cycle-time medians. | 01 Sep 2026 | 08 Sep 2026 | 6 | Backend engineer | Parallel
P9 | Client - public site | Landing, reference, transparency board, public problem statements, startup registry, proven solutions, registration and sign-in. | 25 Aug 2026 | 05 Sep 2026 | 10 | Frontend engineer | Parallel
P10 | Client - role workspaces | Seven role-aware workspaces across thirty-one routes: authoring, discovery, scoring, pilot monitoring, procurement, payments, grievance, audit and administration. | 01 Sep 2026 | 12 Sep 2026 | 10 | Frontend engineer | Parallel
P11 | Seed dataset | A deterministic dataset that exercises every state in the workflow, so a reviewer sees the whole lifecycle without clicking through it. | 08 Sep 2026 | 12 Sep 2026 | 5 | Backend engineer | Parallel
P12 | End-to-end test suite | Thirty-two assertions across all five stages and the cross-cutting controls, against a live API on a throwaway database. | 10 Sep 2026 | 17 Sep 2026 | 6 | QA lead | Sequential
P13 | Document set | The ten-document PM-SETU set with a live traceability chain from Charter to Risk Register. | 15 Sep 2026 | 24 Sep 2026 | 8 | Project manager | Parallel
P14 | Accessibility and security pass | Keyboard traversal, contrast and screen-reader review; dependency audit; secrets and error-disclosure review. | 18 Sep 2026 | 25 Sep 2026 | 6 | QA lead | Parallel
P15 | Hackathon submission and demonstration | Demonstration script, question bank, rehearsal against each role, submission. | 25 Sep 2026 | 30 Sep 2026 | 4 | Project manager | Sequential
P16 | Deployment readiness (post-hackathon) | Live MCA, GSTN and Udyam verification; NIC single sign-on; PostgreSQL; GeM, PFMS and CPPP onboarding; VAPT by a CERT-In empanelled auditor; third-party GIGW audit. | 01 Oct 2026 | 31 Mar 2027 | 130 | Mission Director | Sequential

## Gantt
AVSAR programme - week view
|  | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | Q4 | Q1
Phase | Phase name | 01-07 Jul | 08-14 Jul | 15-21 Jul | 22-28 Jul | 29 Jul-04 Aug | 05-11 Aug | 12-18 Aug | 19-25 Aug | 26 Aug-01 Sep | 02-08 Sep | 09-15 Sep | 16-22 Sep | 23-29 Sep | 30 Sep-06 Oct | Oct-Dec 2026 | Jan-Mar 2027
P1 | Discovery and policy mapping | bar: W1 to W3
P2 | Charter and requirements | bar: W4 to W5
P3 | Data model and workflow design | bar: W6 to W7
P4 | Design system | bar: W7 to W8
P5 | API - identity and challenge | bar: W8 to W9
P6 | API - evaluation and pilot | bar: W9 to W10
P7 | API - procurement and registry | bar: W9 to W10
P8 | Audit and transparency | bar: W10 to W11
P9 | Client - public site | bar: W9 to W10
P10 | Client - role workspaces | bar: W10 to W11
P11 | Seed dataset | bar: W11
P12 | End-to-end test suite | bar: W11 to W12
P13 | Document set | bar: W12 to W13
P14 | Accessibility and security pass | bar: W12 to W13
P15 | Hackathon submission and demonstration | bar: W13 to W14
P16 | Deployment readiness (post-hackathon) | bar: Q4 to Q1
Legend
Sequential - on the critical path
Parallel - overlaps a preceding phase

## Summary
Timeline - summary
Phases planned | Total rows on the Timeline tab
Sequential phases | On the critical path
Parallel phases | Overlap a preceding phase
Total effort (working days) | Sum of phase durations, before overlap
Effort to hackathon submission | Excludes the deployment-readiness phase
Longest phase (days) | Deployment readiness, spanning two quarters
Mean phase length (days) | Indicator of phase granularity
Parallelisation share | Format as a percentage
Distinct owners | Distinct values in the Owner column
Total effort is the sum of phase durations and exceeds elapsed calendar time because nine phases run in parallel. See the Gantt tab for the elapsed view.